## Instructions
Redirect Tracker — Website + Blog Go-Live
How to use this workbook
Two tabs: "Website Redirects" and "Blog Redirects." One row per redirect.
Current Link — the exact old URL as it exists on production today (synnovatia.com).
New Link — the exact destination it should point to once staging goes live.
Notes — leave blank until a row is actually worked; don't pre-fill guesses.
Complete — click the cell, pick ☑ from the dropdown once the redirect is live AND verified.
Verifying a redirect
Don't trust the Redirection plugin's admin UI alone — it's been unreliable before.
From a browser console: fetch(url, {redirect:'manual'}) — a response with type
'opaqueredirect' or status 301 confirms the rule is actually firing.
Rows already filled in are confirmed from the build history — everything else is a
placeholder for tomorrow's audit. See plans/2026-09-03-redirect-audit-plan.md for the
full methodology (how to pull production's real URL list, how to handle the 421 old
blog categories, etc.) before starting.

## Website Redirects
Current Link (Production) | New Link (Staging) | Notes | Complete
/messy-middle-mastermind/ | /mastermind-for-the-messy-middle/ | Confirmed — old slug is what a pre-existing Redirection rule pointed here; had to be disabled once already when it collided with the new page (HISTORY.md 2026-08-16). LIVE 2026-09-06 — loaded into staging's Redirection plugin (already installed, active, in the "Redirections" group) via CSV import, verified via the REST API that it resolved correctly. | ☑
/7-figure-forum-business-coaching-mastermind-synnovatia/ | /seven-figure-forum/ | Confirmed — real facts for the new page were pulled directly from this live production URL (HISTORY.md 2026-08-15). LIVE 2026-09-06 — loaded into staging's Redirection plugin (already installed, active, in the "Redirections" group) via CSV import, verified via the REST API that it resolved correctly. | ☑
(homepage swap — not a redirect) | /homepage-new-design-draft/ becomes the site front page | WordPress "front page" setting, not a Redirection rule. Flagging so it isn't missed on go-live day. | ☐
/monthly-coaching/ | /work-with-me/ | RESOLVED 2026-09-03 — real production page found: "Business Coaching Program" (id 298), excerpt literally opens "Strategic Coaching." Content is now the "Strategic Coaching" section within Work With Me. | ☐
/solutions/ | /work-with-me/ | RESOLVED 2026-09-03 — real production page found: "Solutions on the Fly, Small Business Strategies" (id 305), content matches exactly. Now the "Solutions on the Fly" section within Work With Me. LIVE 2026-09-06 — loaded into staging's Redirection plugin (already installed, active, in the "Redirections" group) via CSV import, verified via the REST API that it resolved correctly. | ☑
(925+ existing Redirection rules on production) | (preserve as-is) | BLOCKED 2026-09-03 — needs Jackie's own production wp-admin login to export (Tools → Redirection → Export); the password manager wasn't connected in this session to do it via credential autofill. Still needs doing before go-live regardless of mechanism chosen. | ☐
Free Business Assessment / Thank You / Contact Form Thank You | same slugs — likely no redirect needed | CONFIRMED 2026-09-03 via direct slug match (production REST vs. staging REST): free-business-assessment, thank-you-core-business-assessment, and contact-form-thank-you all kept identical slugs on staging — no redirect needed. Strategic Business Consultations pulled out to its own row below — it did NOT keep its slug on staging (see note there). | ☑
/strategic-business-consultations/ | /schedule-a-conversation/ | CONFIRMED 2026-09-03 — real production page "Contact Us to Supercharge Your Business Growth." Rebuilt to brand on staging 2026-09-02 at the same slug, but Jackie confirmed today (during the orphaned-page cleanup) it should stay retired/trashed on staging since Schedule a Conversation supersedes it — so this one DOES need a redirect on go-live, unlike the other 3 legacy pages above. LIVE 2026-09-06 — loaded into staging's Redirection plugin (already installed, active, in the "Redirections" group) via CSV import, verified via the REST API that it resolved correctly. | ☑
/schedule-chat/ | /schedule-a-conversation/ | Real production page found 2026-09-03: "Schedule Your Chat with Us Meeting" — the old scheduler page, same function as the new Schedule a Conversation page. High confidence. LIVE 2026-09-06 — loaded into staging's Redirection plugin (already installed, active, in the "Redirections" group) via CSV import, verified via the REST API that it resolved correctly. | ☑
/stage-ii-enterprise-entrepreneur-strategies/ | (retire — no redirect) | DECIDED 2026-09-04 — Jackie confirmed: retire, no redirect target. Will 404 (or be handled via the full-overwrite mechanism, which removes it automatically since it was never on staging). | ☐
/client-cafe-strategy-call-prep-form/ | (retire — no redirect) | DECIDED 2026-09-04 — Jackie confirmed: not needed, will be retired/trashed. No rebuild, no redirect. | ☐
/coaching/ | (retire — no redirect) | DECIDED 2026-09-04 — Jackie confirmed: retire/trash, no redirect target. | ☐
/services/ | (retire — no redirect) | DECIDED 2026-09-04 — Jackie confirmed: retire/trash, no redirect target. | ☐

## Blog Redirects
Current Link (Production) | New Link (Staging) | Notes | Complete
Individual post URLs (all 563) | no change — same URLs | Confirmed multiple times during the rebuild — every post kept its real, existing production URL. No redirect work needed here. | ☑
/business-coaching-blog/ | /business-coaching-blog/ (new content) | Same slug, content swap only — not a URL redirect. Just confirm the new front page is what's live post-cutover. | ☑
/business-coaching-blog/all/ | /business-coaching-blog/all/ (new content) | Same as above for the All Posts page. | ☑
Old /category/<slug>/ archive URLs (421 near-duplicate categories) — TBD, audit needed | one of six /topic/<slug>/ pages, mapped per category | DONE 2026-09-03 — pulled all 421 categories + all 563 posts' category assignments from production (REST API), cross-referenced against outputs/website-redesign/2026-08-16-blog-topic-classification.csv's per-post topic mapping. Full breakdown: 48 categories have 2+ posts with a clear (≥60%) majority topic — real redirect candidates, listed below. 31 categories have 2+ posts but a genuinely mixed/split topic assignment (no majority) — these need a human call, not an algorithmic guess (see outputs/website-redesign/2026-09-03-category-to-topic-mapping.csv for the full breakdown of each). 311 categories have exactly 1 post and 31 have zero — confirms the "421 near-duplicate categories" problem is real; these 342 are almost certainly negligible-traffic and not worth redirecting individually without Search Console data confirming otherwise (no GA/Search Console access in this session to verify). UPDATE 2026-09-06: the 31 ambiguous categories are now resolved too, using each category's own slug wording as the tie-break signal (e.g. "sales-client-acquisition-marketing" -> Sales & Marketing, "best-practices-attitude" -> Mindset & Resilience) since the per-post vote was genuinely split on all of them. Proposal for Jackie to review/override, not a final call — see outputs/website-redesign/2026-09-06-ambiguous-category-resolutions.csv for the full reasoning per category. Added as rows below, appended after the 48 high-confidence ones. | ☐
/category/human-resources/ | https://synnovatiacom.stage.site/topic/people-partnerships/ | 26 posts, 96% mapped to People & Partnerships | ☑
/category/productivity/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 6 posts, 67% mapped to Strategy & Planning | ☑
/category/business-planning-business-growth/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 5 posts, 60% mapped to Strategy & Planning | ☑
/category/work-life-balance-productivity-performance/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 5 posts, 60% mapped to Mindset & Resilience | ☑
/category/business-success-goal-achievement-best-practices/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 5 posts, 60% mapped to Strategy & Planning | ☑
/category/attitude/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 5 posts, 100% mapped to Mindset & Resilience | ☑
/category/small-business-growth/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 5 posts, 60% mapped to Growth & Scaling | ☑
/category/small-business-blogging/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 5 posts, 100% mapped to Sales & Marketing | ☑
/category/finances/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 5 posts, 100% mapped to Strategy & Planning | ☑
/category/strategic-coaching/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 5 posts, 100% mapped to Ownership & Entrepreneurship | ☑
/category/uncategorized/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 4 posts, 75% mapped to Mindset & Resilience | ☑
/category/small-business-growth-growth-strategies-small-business-success/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 4 posts, 75% mapped to Growth & Scaling | ☑
/category/business-coaching/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 4 posts, 75% mapped to Ownership & Entrepreneurship | ☑
/category/work-life-balance-performance/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 4 posts, 75% mapped to Mindset & Resilience | ☑
/category/inbound-marketing-small-business-blogging-content-marketing/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 4 posts, 100% mapped to Sales & Marketing | ☑
/category/productivity-time-management-performance/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 4 posts, 75% mapped to Strategy & Planning | ☑
/category/strategic-thinking/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 3 posts, 67% mapped to Strategy & Planning | ☑
/category/best-practices/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 3 posts, 67% mapped to Ownership & Entrepreneurship | ☑
/category/entrepreneurship/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 3 posts, 67% mapped to Growth & Scaling | ☑
/category/best-practices-business-growth-entrepreneurship/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 3 posts, 67% mapped to Growth & Scaling | ☑
/category/business-growth-success-psychology/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 3 posts, 67% mapped to Mindset & Resilience | ☑
/category/strategic-coaching-business-coaching/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 3 posts, 100% mapped to Ownership & Entrepreneurship | ☑
/category/performance/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 3 posts, 67% mapped to Ownership & Entrepreneurship | ☑
/category/small-business-success-best-practices-entrepreneurship/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 3 posts, 67% mapped to Strategy & Planning | ☑
/category/small-business-growth-best-practices/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 3 posts, 100% mapped to Growth & Scaling | ☑
/category/performance-motivation/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 3 posts, 100% mapped to Mindset & Resilience | ☑
/category/business-planning-strategic-coaching/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 3 posts, 67% mapped to Growth & Scaling | ☑
/category/business-skills-growth-strategy-small-business-success/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, 100% mapped to Strategy & Planning | ☑
/category/mastermind-group/ | https://synnovatiacom.stage.site/topic/people-partnerships/ | 2 posts, 100% mapped to People & Partnerships | ☑
/category/best-practices-performance-attitude/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, 100% mapped to Mindset & Resilience | ☑
/category/business-skills-motivation-success-psychology/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, 100% mapped to Mindset & Resilience | ☑
/category/small-business-strategy/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, 100% mapped to Strategy & Planning | ☑
/category/small-business-start-up/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 2 posts, 100% mapped to Ownership & Entrepreneurship | ☑
/category/work-life-balance/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, 100% mapped to Mindset & Resilience | ☑
/category/performance-attitude/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, 100% mapped to Mindset & Resilience | ☑
/category/small-business-success-human-resources/ | https://synnovatiacom.stage.site/topic/people-partnerships/ | 2 posts, 100% mapped to People & Partnerships | ☑
/category/women-in-business/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 2 posts, 100% mapped to Ownership & Entrepreneurship | ☑
/category/small-business-strategist-small-business-success-strategic-coaching/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 2 posts, 100% mapped to Ownership & Entrepreneurship | ☑
/category/inbound-marketing-small-business-blogging-lead-generation/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 2 posts, 100% mapped to Sales & Marketing | ☑
/category/inbound-marketing-client-acquisition-lead-generation/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 2 posts, 100% mapped to Sales & Marketing | ☑
/category/client-acquisition-marketing-lead-generation/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 2 posts, 100% mapped to Sales & Marketing | ☑
/category/small-business-growth-vendors-entrepreneurship/ | https://synnovatiacom.stage.site/topic/people-partnerships/ | 2 posts, 100% mapped to People & Partnerships | ☑
/category/best-practices-client-acquisition-client-service/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 2 posts, 100% mapped to Sales & Marketing | ☑
/category/vendors-growth-strategies-small-business-success/ | https://synnovatiacom.stage.site/topic/people-partnerships/ | 2 posts, 100% mapped to People & Partnerships | ☑
/category/small-business-growth-best-practices-business-planning/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, 100% mapped to Strategy & Planning | ☑
/category/small-business-growth-business-planning/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, 100% mapped to Strategy & Planning | ☑
/category/work-life-balance-productivity-time-management/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, 100% mapped to Mindset & Resilience | ☑
/category/sales/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 2 posts, 100% mapped to Sales & Marketing | ☑
/category/business-growth/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 13 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/productivity-performance/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 7 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/business-skills/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 6 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/business-growth-small-business-strategy/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 6 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/growth-strategies-best-practices/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 4 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/performance-motivation-attitude/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 4 posts, split vote resolved via slug wording -> Mindset & Resilience (Jackie to confirm/override) | ☑
/category/growth-strategies-best-practices-business-planning/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 4 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/small-business-growth-business-coaching/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 3 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/productivity-best-practices-performance/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 3 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/growth-strategies-best-practices-strategic-coaching/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 3 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/business-growth-mastermind-group/ | https://synnovatiacom.stage.site/topic/people-partnerships/ | 2 posts, split vote resolved via slug wording -> People & Partnerships (Jackie to confirm/override) | ☑
/category/business-skills-small-business-success-performance/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/growth-strategy-time-management-performance/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/best-practices-attitude/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, split vote resolved via slug wording -> Mindset & Resilience (Jackie to confirm/override) | ☑
/category/small-business-success-best-practices-success-psychology/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, split vote resolved via slug wording -> Mindset & Resilience (Jackie to confirm/override) | ☑
/category/best-practices-business-growth/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 2 posts, split vote resolved via slug wording -> Sales & Marketing (Jackie to confirm/override) | ☑
/category/best-practices-performance/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/small-business-success/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 2 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/business-vision/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/strategic-business-coaching/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 2 posts, split vote resolved via slug wording -> Ownership & Entrepreneurship (Jackie to confirm/override) | ☑
/category/small-business-growth-small-business-success/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 2 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/small-business-growth-performance/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 2 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/sales-client-acquisition-marketing/ | https://synnovatiacom.stage.site/topic/sales-marketing/ | 2 posts, split vote resolved via slug wording -> Sales & Marketing (Jackie to confirm/override) | ☑
/category/small-business-growth-small-business-success-growth-advisor/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 2 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/small-business-growth-small-business-success-motivation/ | https://synnovatiacom.stage.site/topic/growth-scaling/ | 2 posts, split vote resolved via slug wording -> Growth & Scaling (Jackie to confirm/override) | ☑
/category/small-business-success-entrepreneurship-success-psychology/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, split vote resolved via slug wording -> Mindset & Resilience (Jackie to confirm/override) | ☑
/category/productivity-growth-strategies-performance/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/productivity-performance-motivation/ | https://synnovatiacom.stage.site/topic/mindset-resilience/ | 2 posts, split vote resolved via slug wording -> Mindset & Resilience (Jackie to confirm/override) | ☑
/category/best-practices-business-planning/ | https://synnovatiacom.stage.site/topic/strategy-planning/ | 2 posts, split vote resolved via slug wording -> Strategy & Planning (Jackie to confirm/override) | ☑
/category/performance-strategic-coaching/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 2 posts, split vote resolved via slug wording -> Ownership & Entrepreneurship (Jackie to confirm/override) | ☑
/category/best-practices-strategic-coaching/ | https://synnovatiacom.stage.site/topic/ownership-entrepreneurship/ | 2 posts, split vote resolved via slug wording -> Ownership & Entrepreneurship (Jackie to confirm/override) | ☑